## Slide 1
UWinsite Student - Update
Alice Miller
University Registrar
UWinsite Student Lead
Administrative Heads
July 18, 2018

## Slide 2: For Today
Where we are….
Where we are going….
First days in the new system….
Proposed registration schedule
Sample business changes
System Fundamentals
Demo….

## Slide 3
On
Track
Go-Live Date: November 26, 2018
Many tools to manage & track activities
MS Project Daily Scrums
PMC, ALM Systems Heat Maps
SharePoint SPI Index
Release
Go- Live
UAT
SIT2
SIT1
CIT3
CIT2
CIT1
We are here

## Slide 4: Project Update
May - July
Critical configuration complete/unit tested; secondary configuration nearing completion
Academic Advisement (2011)
System Security
Business Process Planning
SIT scenario development
ONGOING COMMUNICATION WITH ALL STAKEHOLDERS
TRAINING Sep ’18 onwards
System Integration Testing
July 9- Sep 21
End-to-end testing of the critical build by the core team
Report development
Secondary configuration complete
User Acceptance Testing
Sept 24 - Oct 25
End-to-end testing by key UWindsor personnel
Report development continues
Go Live!
Oct – Nov 26
Cutover/Go Live plan designed / implemented
Go Live!
Support
Process changes operationalized

## Slide 5: SIT Faculty of Nursing Example
Business Process | Scenario | Navigation | Task Description
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Career and Program Information:Process Student Groups | Add Student Group NURS to students to be block enrolled in clinical courses using an external file load
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Term Processing>Term Activation>Term Activation Batch Process | Run Term Activation Batch process to term activate nursing students in the NURS Student Group
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Student Term Information>Term Activate a Student | Verify that term was activated by checking some of the students in the nursing group.
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Enroll Students>Block enrollment>Create Class Block | Verify class block exist with correct courses
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Enroll Students>Block enrollment>Create Student Block | Verify student block exist with correct students Selection tool: External File Upload file : Choose CVS file File Mapping: Nursing Hit Preview Selection Results
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Enroll Students>Block enrollment>Block Enroll Merge | Add New Value Academic Institution : UWin1 Choose the Student and Class Block Click Merge Hit Submit
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Curriculum Management>Class Roster> Class Roster | Validate that students are registered on class roster
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Enroll Students>Block enrollment>Create Class Block | Verify class block exist with correct courses
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Enroll Students>Enrollment | Verify that students were registered in the correct block of courses.
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Term Processing>Appointments>Assign Appointments | Assign Appointment times to Nursing students to be registered in clinicals
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Term Processing>Appointments>Student Enrollment Appointment | Check that the correct registration appointment time was applied
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Student Term Information>Update Enrollment Limits | Update enrolment limits for 2nd and 3rd year Nursing students block enrolled in clinical courses
Manage Enrollments | Adjust Program level enrollment limits for Nursing and enroll | Main Menu > Records and Enrollment > Student Term Information > Update Enrollment Limits | Find an existing run control and if none exist create a new one. Check the Population Selection box. Select 'PS Query" in Selection Tool field. Select correct query. Click on Edit Prompts link and input TERM. Preview Selection Results and record a student number from the list. Check the Override Unit Limits box; input 18 in the Max Total Units field. Click Run
Manage Enrollments | Adjust Program level enrollment limits for Nursing and enroll | Main Menu > Records and Enrollment > Student Term Information > Term Activate a Student > Enrollment Limit Tab | Confirm student's Max Total Units has changed to 18
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Records and Enrollment>Student Term Information>Term Activate a Student | Check that maximum FT load was updated for the nursing students in 2nd and 3rd year block enrolled in clinical courses
Manage Enrollments | Enrol nursing students in winter clinicals prior to reg appt time then run term limits (validation/appointment times) | Student Self Service | Register nursing students in the rest of their courses through SSS. Include a course that would conflict with a clinical course. Include all courses up to the increased max load limit

## Slide 6: November 26th
Students will have access to their program planner
  Registration will begin November 30th
  Registration will not conflict with final examinations
Resources will be available across the campus to assist in the use of the tool

## Slide 7
Winter 2019 Proposed Registration Times |  |  |  |  | 
Category | SubCategory | Anticipated Registration Load | 2019 start date | Sum per day | Start time
NEW |  | 600 | 30-Nov-18 |  | 9:00
NEWG (incuding M.Eng) |  | 600 | 30-Nov-18 |  | 9:00
MBA |  | 55 | 30-Nov-18 |  | 9:00
DE |  | 100 | 30-Nov-18 |  | 9:00
GRAD Non Meng |  | 1950 | 30-Nov-18 |  | 11:20
ATH |  | 330 | 30-Nov-18 |  | 14:00
CEPE |  | 1000 | 30-Nov-18 |  | 14:00
Returning Nursing | SM5 | 360 | 30-Nov-18 | 4995 | 19:00
MSWP |  | 220 | 03-Dec-18 |  | 9:00
Meng Returning |  | 1250 | 03-Dec-18 |  | 9:00
UGrad | 38 + | 900 | 03-Dec-18 |  | 9:50
UGrad | 35-38 | 900 | 03-Dec-18 |  | 11:20
Returning Nursing | SM7 | 340 | 03-Dec-18 |  | 12:00
Returning Nursing | SM3 | 140 | 03-Dec-18 |  | 12:00
UGrad | 30-35 | 1000 | 03-Dec-18 |  | 15:50
Degree completion 2yr | 20 + | 40 | 03-Dec-18 | 4790 | 15:50
UGrad | 26-30 | 880 | 04-Dec-18 |  | 9:50
UGrad | 24-26 | 950 | 04-Dec-18 |  | 11:20
UGrad | 19-24 | 1100 | 04-Dec-18 |  | 12:50
Degree completion 2yr | 10-20 | 20 | 04-Dec-18 |  | 12:50
Degree completion 3yr | 10 + | 50 | 04-Dec-18 |  | 12:50
UGrad | 16-19 | 800 | 04-Dec-18 |  | 14:00
Degree completion 3yr | 0-10 | 20 | 04-Dec-18 |  | 14:00
Degree completion 2yr | 0-10 | 100 | 04-Dec-18 |  | 14:00
Returning Nursing | SM1 | 120 | 04-Dec-18 |  | 15:50
UGrad5 (Engineering) | ENG | 400 | 04-Dec-18 | 4380 | 15:50
UGrad | 14-16 | 900 | 05-Dec-18 |  | 9:50
UGrad | 6-14 | 1000 | 05-Dec-18 |  | 11:20
UGrad | 5-6 | 800 | 05-Dec-18 |  | 12:50
UGrad5 (Business/HK) | BUS-HK | 400 | 05-Dec-18 |  | 12:50
UGrad | 0-5 | 1600 | 05-Dec-18 |  | 14:00
Non Degree |  | 170 | 05-Dec-18 | 4870 | 15:50
EDUC |  | 500 | 10-Dec-18 |  | 9:00
LAW | LW5 | 220 | 02-Jan-19 |  | 9:00
LAW | LW3 | 230 | 03-Jan-19 |  | 9:00

## Slide 8: Example changes to our business:
Offer letters will be online
All course work completed at other PSI’s will be in the system
Service Indicators
  Financially ineligible
Minors/Specializations through self-service
Waitlists
Concurrent Education students GPA’s
Infosilem
  Final exam schedule – Winter 2019
  Timetabling – Fall 2019

## Slide 9
System Fundamentals

## Slide 10: Academic & program structure
Institution
University
(UWIN1)
Academic Group
Faculty
Plan
Major, Minor
Sub Plan
Tracks within major e.g. co-op, thesis
”I’m doing an Honours BSc” (the degree that is attached to the plan)
“It’s a BSc in Chemistry” (the Chemistry is the plan)
”with a Music minor” (that’s another Plan)
Academic ”Org” (Organization)
Department
That’s a Program/Plan Stack!
Career
Undergrad, Grad, Law, Education

## Slide 11: Course Codes
http://www.uwindsor.ca/registrar/courses/translation
03-60-104
Subject Code
Course Number
Subject Code
Catalog Number
Current
Course Code
COMP-1047
New
Course Code

## Slide 12
Let’s head to the construction site…

## Slide 13: Questions and feedback are always welcome!
uwinsite@uwindsor.ca
http://www.uwindsor.ca/uwinsite