Office of Quality Assurance

SUGGESTED WORKFLOW BREAKDOWN – TIMELINE FOR 2022/23 IQAP CYCLICAL REVIEWS

|  | Deadlines/milestones | Suggested AAU tasks |
| --- | --- | --- |
| March – April 2022 | - Orientation meeting with AAU Head - QA office attends AAU Council meeting | • AAU to review required documentation templates and instructions, establish AAU review team(s), assign responsibilities and set interim due dates (see ‘delegation of tasks’ document) • complete Table 8 “Faculty members by program/field”, distribute faculty CV instructions to faculty members and begin compiling faculty CVs (see Faculty CV instructions) • survey faculty members for potential external reviewer nominees (see External reviewer instructions) |
| May – June 2022 | Workshop& ongoing progress meetings with AAU review team(s) and key individuals to work on cyclical program review development. June 24, 2022 – Proposed External Reviewer nominees due – Faculty CVs – first draft due | • identify all stakeholders (students, faculty, staff, other AAUs for combined programs, any partner institutions, etc.) and plan methods for soliciting stakeholders’ feedback (e.g. surveys, focus groups). Begin developing survey/focus group questions. Submit to QA office application for ethical review of surveys (under the expedited IQAP Ethics Board process). Review available departmental data, e.g. NSSE. • request from Finance/Faculty Administrative Officer Table 14 “Internal operating funding” • request report on holdings from Leddy Library • request report from Space Mgmt office • work on Table 7a and b “Projected intake and enrolment for Undergraduate (a) and Graduate (b) for the next 7 yrs” • work on Table 1a and b– “Undergraduate and Graduate Program Learning Outcomes” for all programs under review and curriculum mapping: review existing program and course learning outcomes and revise as needed. |
| July – August 2022 | August 26, 2022: - Faculty CVs - second (final) draft due | • work on suggested revisions on faculty CVs and finalize faculty CVs • work on self-study sections due for 1st draft (see Cyclical Program Review Flowchart) • begin compiling self-study Appendices (course syllabi; program Learning outcomes; course descriptions, student handbook, etc.) |
| Sept.-Oct. 2022 | September 30, 2022: - Self-study 1st draft due | • as tables are provided by QA office, work on analytical sections to comment on data in tables • work on self-study 1st draft revisions • summarize survey findings and stakeholders’ feedback. |
| Nov-Dec 2022 | November 25, 2022 - Self-study 2nd (final) draft due | • work on finalizing / updating analytical sections and comments based on all tables provided by QA office |
|  |  | • Submit final version of self-study to QA office • work on last updates and finalize self-study |
| Feb-April 2023 | Site visit |  |